## Ex. schedule vacc by location
VACCINATION SCHEDULE BY LOCATION. Amidou District.
12 core vaccination teams available (1 vaccinator + 2 preparers + registrars, recoder and security staff)
Locations | Target pop. | Nb of teams | Duration (in days) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
MARCOTTE - Central square | 10987 | 2 | 5 | D1: 2; D2: 2; D3: 2; D4: 2; D5: 2
MARCOTTE - Matete school | 9923 | 2 | 5 | D1: 2; D2: 2; D3: 2; D4: 1; D5: 2
MARCOTTE - School no 2 | 8654 | 2 | 4 | D1: 2; D2: 2; D3: 2; D4: 2
MARCOTTE - House of the people | 4216 | 1 | 4 | bar: D1 to D5
ZABOUBOU - School no 1 | 11021 | 2 | 5 | D3: 2; D4: 2; D5: 2; D6: 2; D7: 2
ZABOUBOU - Central square | 10367 | 2 | 5 | D3: 2; D4: 2; D5: 2; D6: 2; D7: 2
ZABOUBOU - Union square | 5432 | 1 | 5 | bar: D3 to D8
ESPACALOU - Central square | 4136 | 1 | 4 | bar: D7 to D14
SWITCHE - Central square | 3986 | 1 | 4 | bar: D7 to D14
BAROUELI - Lemba square | 4080 | 1 | 4 | bar: D7 to D14
BAROUELI - School no 1 | 4384 | 1 | 4 | bar: D7 to D14
TOTAL | 77186 |  |  | 7 | 7 | 12 | 11 | 9 | 5 | 9 | 4 | 4 | 4 | 0 | 0 | 0 | 0
Extra days if required
Day off/debriefing/preparation

## Ex. schedule vacc by team
VACCINATION SCHEDULE BY TEAM. Amidou District
12 core vaccination teams available (1 vaccinator + 2 preparers + registrars, recoder and security staff)
TEAMS | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15
Team A | D1: MARCOTTE - Central square; D7: ESPACALOU - Central square
Team B | D1: MARCOTTE - Central square; D7: SWITCHE - Central square
Team C | D1: MARCOTTE - Matete school; D7: BAROUELI - Lemba square
Team D | D1: MARCOTTE - Matete school; D7: BAROUELI - School no 1
Team E | D1: MARCOTTE - School no 2
Team F | D1: MARCOTTE - School no 2
Team G | D1: MARCOTTE - House of the people
Team H | D3: ZABOUBOU - School no 1
Team I | D3: ZABOUBOU - School no 1
Team J | D3: ZABOUBOU - Central square
Team K | D3: ZABOUBOU - Central square
Team L | D3: ZABOUBOU - Union square
| Day off/debriefing/preparation |  |  |  | Extra days if required

## Ex. freezing capacity
23 - ESTIMATING NEEDS - FREEZING CAPACITY for a vaccination campaign
The volume and freezing capacity needed depend primarily on the number of vaccination sites, the number of vaccination teams per site, and the schedule and duration of the campaign (see sheets "Vaccination schedule by location" and "Vaccination schedule by team").
1) Il faut en premier lieu définir les besoins en glace pour chaque site. Une glacière RCW 25 permet de transporter environ 5000 doses de vaccin avec le solvent. Sachant que l'on estime les performances d'un vaccinateur a environ 1500 vaccinations par jou
FILL IN ONLY THE YELLOW BOXES. Calculations will appear automatically.
1) Define the cold chain equipment for one vaccination site
One vaccination site can accommodate one or two teams, at most (1 to 2 vaccinators, and 2 preparers per vaccinator).
One vaccinator can vaccinate, on average 800 to 1000 vaccinations per day in urban area and 300 to 600 in rural area.
Determine the cold-chain needs for each team:
1 RCW 25 cold box (20.4 litres) can store 3300 (3 cm3/dose) to 5000 (2 cm3/dose) doses of vaccine and solvent, and requires:
► At ambient temperatures below 40°C: 12 0.6-litre ice packs to be replaced every 2 days or 14 0.6-litre ice packs to be replaced every 3 days. Note: never use fewer than 12 0.6-litre ice packs.
► At ambient temperatures above 40°C: 12 0.6-litre ice packs to be replaced every day or 18 0.6-litre ice packs to be replaced every 2 days or 24 0.6-litre ice packs to be replaced every 3 days.
1 Giostyle-type vaccine carrier for 2 preparers can store 500 (3 cm3/dose) to 750 (2 cm3/dose) doses of vaccine and solvent, and requires:
► At ambient temperatures below 40°C: 6 0.4-litre ice packs, to be replaced every day.
► At ambient temperatures above 40°C: 8 0.4-litre ice packs, to be replaced every day.
Additional ice packs and vaccine doses can be supplied by the logistics team during the day, according to needs.
|  |  |  | 3 | 2
2
Check the box corresponding to the outside temperature
Check the box corresponding to the interval for replacing ice packs in the RCW25 cold boxes
The tables below change automatically as a function of the temperature and replacement interval.
Table A: Automatic calculation of the needs for 1 or 2 teams at one site.
PASSIVE COLD CHAIN EQUIPMENT PER SITE |  | Nb of cold boxes and vaccine carriers per team | Nb of ice packs per cold box and vaccine carrier |  |  | Total nb of ice packs on D1 | Volume of ice packs
1 RCW 25 cold-box (vaccines and diluents) |  | 1 | 24 |  |  | 24 | 0,6 l
Vaccine carrier Giostyle for 1 team |  | 1 | 8 |  |  | 8 | 0,4 l
Vaccine carrier Giostyle for 2 teams |  | 2 | 8 |  |  | 16 | 0,4 l
Table B: Automatic calculation of the number of ice packs needed per day for 1 or 2 teams at one site. These numbers are transferred to the table in point 2.
Rythmn and number of ice packs needed
|  |  | D1 | D2 | D3 | D4 | D5
Nb of ice packs required for 1 team per site |  |  | 32 | 8 | 8 | 32 | etc.
Nb of ice packs required for 2 teams per site |  |  | 40 | 16 | 16 | 40 | etc.
2) Estimate the number of ice packs needed each day for all of the teams and sites
Enter the names of the locations and sites (one line per site), the number of teams per site and their identification
Then transfer the number of ice packs needed per day and per site according to the data in Table B (above).
District: | Amidou
Table C
Towns/locations and sites | Number of teams | Team | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23
Marcotte Central square | 2 | A and B | D1: 34; D2: 16; D3: 34; D4: 16; D5: 34
Marcotte Matete school | 2 | C and D | D1: 34; D2: 16; D3: 34; D4: 16; D5: 34
Marcotte School n°2 | 2 | E and F | D1: 34; D2: 16; D3: 34; D4: 16
Marcotte House of the people | 1 | G | D1: 26; D2: 8; D3: 26; D4: 8
Zaboulou School n°1 | 2 | H and I | D3: 34; D4: 16; D5: 34; D6: 16; D7: 34
Zaboulou Central square | 2 | J and K | D3: 34; D4: 16; D5: 34; D6: 16; D7: 34
Zaboulou Union Square | 1 | L | D3: 26; D4: 8; D5: 26; D6: 8; D7: 8
BAROUELI - Lemba square | 1 | C | D7: 26; D8: 8; D9: 26; D10: 8
BAROUELI - School no 1 | 1 | D | D7: 26; D8: 8; D9: 26; D10: 8
SWITCHE - Cental square | 1 | B | D7: 26; D8: 8; D9: 26; D10: 8
ESCAPALOU - Cental square | 1 | A | D7: 26; D8: 8; D9: 26; D10: 8
TOTAL number of ice packs needed per day |  |  | 128 | 56 | 222 | 96 | 162 | 40 | 180 | 32 | 104 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) Determine the available and required freezing capacities
From the inventory, fill in one line in Table D for each type of working freezer available.
Indicate for each brand and type of freezer: number and specifications (freezing capacicty and volume in litres).
3 types of freezers VESTFROST are proposed. Add the other types of freezers available and enter the specifications: freezing capacicty and volume (yellow boxes)
Table D
Brand and model | Number | Freezing capacity | D2: Storage
|  |  |  | Volume (litres) |  | Number of ice packs
|  | Kg/24 hrs | D1: No. of 0.6 l ice packs/24 hrs; D2: Per freezer; D3: Total; D4: Per freezer; D5: Total
VESTFROST MF 314 | 1 | 32.4 | D1: 54; D2: 323; D3: 323; D4: 323; D5: 323
VESTFROST MF 214 |  | 22.3 | D1: 0; D2: 213; D3: 0; D4: 213; D5: 0
VESTFROST MF 114 |  | 17.5 | D1: 0; D2: 111; D3: 0; D4: 111; D5: 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
TOTAL |  | 72.2 | D1: 54; D2: 647; D3: 323; D4: 647; D5: 323
According to the inventory of available freezers for the campaign:
It is possible to freeze | 54 | ice packs per day
It is possible to store | 323 | ice packs in total
Number of days required to freeze all the ice packs for Day 1 |  |  | D2: 5.9815; D3: Note:; D5: Do not exceed the 24-hour freezing capacity of the freezers.
Put in half of the ice packs to freeze in the morning and the other half at night.
4) Ice-packs needs per day for sites
On D1, note the maximum number of ice packs that can be stored (H85, B89) or the maximum number of frozen ice packs available on D1. Any negative quantity means that there will not be enough ice packs to supply all the teams.
|  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24
| Balance (1) | 323 | 249 | 175 | 173 | 5 | -37 | -145 | -131 | -257 | -235 | -285 | -263 | -209 | -155 | -101 | -47 | 7 | 61 | 115 | 169 | 223 | 277 | 331 | 385
| Out (2) | 128 | 56 | 222 | 96 | 162 | 40 | 180 | 32 | 104 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In (3) | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
(1) BALANCE = number of available ice packs.
(2) OUT = total number of ice packs supplied to the teams on vaccination sites per day (see point 2).
(3) IN = total number of ice packs that can be frozen per day (see point 3, freezing capacity per 24 h).
Notes | bar: D1 to D11
The performance of all the freezers enables the supply of ice packs to all the sites for 5 days. | bar: D1 to D11
On Day 6, the balance is less than the needs. It is no longer possible to supply the all sites. | bar: D1 to D11
The freezing capacity must be increased (additional freezer and/or other sources of supply) in order to supply all the sites for 10 days, as anticipated in the schedule. | bar: D1 to D11
Note on C96: Note: when the cell becomes gray and the number in black is crossed out, the amount is greater than the number of ice packs cells that can be stored (cells H85, B89).
Température supérieure à 40°C
Température inférieure à 40°C
1 jour
2 jours
3 jours

## Freezing capacity A
ESTIMATING NEEDS - FREEZING CAPACITY for a vaccination campaign
The volume and freezing capacity needed depend primarily on the number of vaccination sites, the number of vaccination teams per site, and the schedule and duration of the campaign (see sheets "Vaccination schedule by location" and "Vaccination schedule by team").
1) Il faut en premier lieu définir les besoins en glace pour chaque site. Une glacière RCW 25 permet de transporter environ 5000 doses de vaccin avec le solvent. Sachant que l'on estime les performances d'un vaccinateur a environ 1500 vaccinations par jou
FILL IN ONLY THE YELLOW BOXES. Calculations will appear automatically.
1) Define the cold chain equipment for one vaccination site
One vaccination site can accommodate one or two teams, at most (1 to 2 vaccinators, and 2 preparers per vaccinator).
One vaccinator can vaccinate, on average 800 to 1000 vaccinations per day in urban areas and 300 to 600 in rural areas.
Determine the cold-chain needs for each team:
1 RCW 25 cold box (20.4 litres) can store 3300 (3 cm3/dose) to 5000 (2 cm3/dose) doses of vaccine and solvent, and requires:
► At ambient temperatures below 40°C: 12 0.6-litre ice packs to be replaced every 2 days or 14 0.6-litre ice packs to be replaced every 3 days. Note: never use fewer than 12 0.6-litre ice packs.
► At ambient temperatures above 40°C: 12 0.6-litre ice packs to be replaced every day or 18 0.6-litre ice packs to be replaced every 2 days or 24 0.6-litre ice packs to be replaced every 3 days.
1 Giostyle-type vaccine carrier for 2 preparers can store 500 (3 cm3/dose) to 750 (2 cm3/dose) doses of vaccine and solvent, and requires:
► At ambient temperatures below 40°C: 6 0.4-litre ice packs, to be replaced every day.
► At ambient temperatures above 40°C: 8 0.4-litre ice packs, to be replaced every day.
Additional ice packs and vaccine doses can be supplied by the logistics team during the day, according to needs.
|  |  |  | 3 | 2
2
Check the box corresponding to the outside temperature
Check the box corresponding to the interval for replacing ice packs in the RCW25 cold boxes
The tables below change automatically as a function of the temperature and replacement interval.
Table A: Automatic calculation of the needs for 1 or 2 teams at one site.
PASSIVE COLD CHAIN EQUIPMENT PER SITE |  | Nb of cold boxes and vaccine carriers per team | Nb of ice packs per cold box and vaccine carrier |  |  | Total nb of ice packs on D1 | Volume of ice packs
1 RCW 25 cold-box (vaccines and diluents) |  | 1 | 24 |  |  | 24 | 0.6 l
Vaccine carrier Giostyle for 1 team |  | 1 | 8 |  |  | 8 | 0.4 l
Vaccine carrier Giostyle for 2 teams |  | 2 | 8 |  |  | 16 | 0.4 l
Table B: Automatic calculation of the number of ice packs needed per day for 1 or 2 teams at one site. These numbers are transferred to the table in point 2.
Rythmn and number of ice packs needed
|  |  | D1 | D2 | D3 | D4 | D5
Nb of ice packs required for 1 team per site |  |  | 32 | 8 | 8 | 32 | etc.
Nb of ice packs required for 2 teams per site |  |  | 40 | 16 | 16 | 40 | etc.
2) Estimate the number of ice packs needed each day for all of the teams and sites
Enter the names of the locations and sites (one line per site), the number of teams per site and their identification
Then transfer the number of ice packs needed per day and per site according to the data in Table B (above).
District:
Table C
Towns/locations and sites | Number of teams | Team n° | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23
TOTAL number of ice packs needed per day |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) Determine the available and required freezing capacities
From the inventory, fill in one line in Table D for each type of working freezer available.
Indicate for each brand and type of freezer: number and specifications (freezing capacicty and volume in litres).
3 types of freezers VESTFROST are proposed. Add the other types of freezers available and enter the specifications: freezing capacicty and volume (yellow boxes)
Table D
Brand and type | Number | Freezing capacity | D2: Storage
|  |  |  | Volume (litres) |  | Nb of ice packs
|  | Kg/24 h | D1: Nb ice packs 0.6 l/24 h; D2: Per freezer; D3: Total; D4: Per freezer; D5: Total
VESTFROST MF 314 |  | 32.4 | D1: 0; D2: 323; D3: 0; D4: 323; D5: 0
VESTFROST MF 214 |  | 22.3 | D1: 0; D2: 213; D3: 0; D4: 213; D5: 0
VESTFROST MF 114 |  | 17.5 | D1: 0; D2: 111; D3: 0; D4: 111; D5: 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
TOTAL |  | 72.2 | D1: 0; D2: 647; D3: 0; D4: 647; D5: 0
According to the inventory of available freezers for the campaign:
It is possible to freeze | 0 | ice packs per day
It is possible to store | 0 | ice packs in total
Number of days required to freeze all the ice packs for Day 1 |  |  | D2: #DIV/0!; D3: Note:; D5: do not exceed the freezers' freezing capacity per 24 hours.
Put in half of the ice packs to freeze in the morning and the other half at night.
4) Evolution of ice-packs needs per day for sites
On D1, note the maximum number of ice packs that can be stored (H85, B89) or the maximum number of frozen ice packs available on D1. Any negative quantity means that there will not be enough ice packs to supply all the teams.
|  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24
| Balance (1) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Out (2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In (3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(1) BALANCE = number of available ice packs.
(2) OUT = total number of ice packs supplied to the teams on vaccination sites per day (see point 2).
(3) IN = total number of ice packs that can be frozen per day (see point 3, freezing capacity per 24 h).
Notes | bar: D1 to D10
The performance of all the freezers enables the supply of ice packs to all the sites for 5 days. | bar: D1 to D10
On Day 6, the balance is less than the needs. It is no longer possible to supply the all sites. | bar: D1 to D10
The freezing capacity must be increased (additional freezer and/or other sources of supply) in order to supply all the sites for 10 days as initially planned. | bar: D1 to D10
Note on C96: Note: when the cell becomes gray and the number in black is crossed out, the amount is greater than the number of ice packs cells that can be stored (cells H85, B89).
Température supérieure à 40°C
Température inférieure à 40°C
1 jour
2 jours
3 jours

## Freezing capacity B
ESTIMATING NEEDS - FREEZING CAPACITY for a vaccination campaign
The volume and freezing capacity needed depend primarily on the number of vaccination sites, the number of vaccination teams per site, and the schedule and duration of the campaign (see sheets "Vaccination schedule by location" and "Vaccination schedule by team").
1) Il faut en premier lieu définir les besoins en glace pour chaque site. Une glacière RCW 25 permet de transporter environ 5000 doses de vaccin avec le solvent. Sachant que l'on estime les performances d'un vaccinateur a environ 1500 vaccinations par jou
FILL IN ONLY THE YELLOW BOXES. Calculations will appear automatically.
1) Define the cold chain equipment for one vaccination site
One vaccination site can accommodate one or two teams, at most (1 to 2 vaccinators, and 2 preparers per vaccinator).
One vaccinator can vaccinate, on average 800 to 1000 vaccinations per day in urban areas and 300 to 600 in rural areas.
Determine the cold-chain needs for each team:
1 RCW 25 cold box (20.4 litres) can store 3300 (3 cm3/dose) to 5000 (2 cm3/dose) doses of vaccine and solvent, and requires:
► At ambient temperatures below 40°C: 12 0.6-litre ice packs to be replaced every 2 days or 14 0.6-litre ice packs to be replaced every 3 days. Note: never use fewer than 12 0.6-litre ice packs.
► At ambient temperatures above 40°C: 12 0.6-litre ice packs to be replaced every day or 18 0.6-litre ice packs to be replaced every 2 days or 24 0.6-litre ice packs to be replaced every 3 days.
1 Giostyle-type vaccine carrier for 2 preparers can store 500 (3 cm3/dose) to 750 (2 cm3/dose) doses of vaccine and solvent, and requires:
► At ambient temperatures below 40°C: 6 0.4-litre ice packs, to be replaced every day.
► At ambient temperatures above 40°C: 8 0.4-litre ice packs, to be replaced every day.
Additional ice packs and vaccine doses can be supplied by the logistics team during the day, according to needs.
|  |  |  | 3 | 2
2
Check the box corresponding to the outside temperature
Check the box corresponding to the interval for replacing ice packs in the RCW25 cold boxes
The tables below change automatically as a function of the temperature and replacement interval.
Table A: Automatic calculation of the needs for 1 or 2 teams at one site.
PASSIVE COLD CHAIN EQUIPMENT PER SITE |  | Nb of cold boxes and vaccine carriers per team | Nb of ice packs per cold box and vaccine carrier |  |  | Total nb of ice packs on D1 | Volume of ice packs
1 RCW 25 cold-box (vaccines and diluents) |  | 1 | 24 |  |  | 24 | 0.6 l
Vaccine carrier Giostyle for 1 team |  | 1 | 8 |  |  | 8 | 0.4 l
Vaccine carrier Giostyle for 2 teams |  | 2 | 8 |  |  | 16 | 0.4 l
Table B: Automatic calculation of the number of ice packs needed per day for 1 or 2 teams at one site. These numbers are transferred to the table in point 2.
Rythmn and number of ice packs needed
|  |  | D1 | D2 | D3 | D4 | D5
Nb of ice packs required for 1 team per site |  |  | 32 | 8 | 8 | 32 | etc.
Nb of ice packs required for 2 teams per site |  |  | 40 | 16 | 16 | 40 | etc.
2) Estimate the number of ice packs needed each day for all of the teams and sites
Enter the names of the locations and sites (one line per site), the number of teams per site and their identification
Then transfer the number of ice packs needed per day and per site according to the data in Table B (above).
District:
Table C
Towns/locations and sites | Number of teams | Team n° | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23
TOTAL number of ice packs needed per day |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) Determine the available and required freezing capacities
From the inventory, fill in one line in Table D for each type of working freezer available.
Indicate for each brand and type of freezer: number and specifications (freezing capacicty and volume in litres).
3 types of freezers VESTFROST are proposed. Add the other types of freezers available and enter the specifications: freezing capacicty and volume (yellow boxes)
Table D
Brand and type | Number | Freezing capacity | D2: Storage
|  |  |  | Volume (litres) |  | Nb of ice packs
|  | Kg/24 h | D1: Nb ice packs 0.6 l/24 h; D2: Per freezer; D3: Total; D4: Per freezer; D5: Total
VESTFROST MF 314 |  | 32.4 | D1: 0; D2: 323; D3: 0; D4: 323; D5: 0
VESTFROST MF 214 |  | 22.3 | D1: 0; D2: 213; D3: 0; D4: 213; D5: 0
VESTFROST MF 114 |  | 17.5 | D1: 0; D2: 111; D3: 0; D4: 111; D5: 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
TOTAL |  | 72.2 | D1: 0; D2: 647; D3: 0; D4: 647; D5: 0
According to the inventory of available freezers for the campaign:
It is possible to freeze | 0 | ice packs per day
It is possible to store | 0 | ice packs in total
Number of days required to freeze all the ice packs for Day 1 |  |  | D2: #DIV/0!; D3: Note:; D5: do not exceed the freezers' freezing capacity per 24 hours.
Put in half of the ice packs to freeze in the morning and the other half at night.
4) Evolution of ice-packs needs per day for sites
On D1, note the maximum number of ice packs that can be stored (H85, B89) or the maximum number of frozen ice packs available on D1. Any negative quantity means that there will not be enough ice packs to supply all the teams.
|  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24
| Balance (1) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Out (2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In (3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(1) BALANCE = number of available ice packs.
(2) OUT = total number of ice packs supplied to the teams on vaccination sites per day (see point 2).
(3) IN = total number of ice packs that can be frozen per day (see point 3, freezing capacity per 24 h).
Notes | bar: D1 to D10
The performance of all the freezers enables the supply of ice packs to all the sites for 5 days. | bar: D1 to D10
On Day 6, the balance is less than the needs. It is no longer possible to supply the all sites. | bar: D1 to D10
The freezing capacity must be increased (additional freezer and/or other sources of supply) in order to supply all the sites for 10 days as initially planned. | bar: D1 to D10
Note on C96: Note: when the cell becomes gray and the number in black is crossed out, the amount is greater than the number of ice packs cells that can be stored (cells H85, B89).
Température supérieure à 40°C
Température inférieure à 40°C
1 jour
2 jours
3 jours

## Freezing capacity C
ESTIMATING NEEDS - FREEZING CAPACITY for a vaccination campaign
The volume and freezing capacity needed depend primarily on the number of vaccination sites, the number of vaccination teams per site, and the schedule and duration of the campaign (see sheets "Vaccination schedule by location" and "Vaccination schedule by team").
1) Il faut en premier lieu définir les besoins en glace pour chaque site. Une glacière RCW 25 permet de transporter environ 5000 doses de vaccin avec le solvent. Sachant que l'on estime les performances d'un vaccinateur a environ 1500 vaccinations par jou
FILL IN ONLY THE YELLOW BOXES. Calculations will appear automatically.
1) Define the cold chain equipment for one vaccination site
One vaccination site can accommodate one or two teams, at most (1 to 2 vaccinators, and 2 preparers per vaccinator).
One vaccinator can vaccinate, on average 800 to 1000 vaccinations per day in urban areas and 300 to 600 in rural areas.
Determine the cold-chain needs for each team:
1 RCW 25 cold box (20.4 litres) can store 3300 (3 cm3/dose) to 5000 (2 cm3/dose) doses of vaccine and solvent, and requires:
► At ambient temperatures below 40°C: 12 0.6-litre ice packs to be replaced every 2 days or 14 0.6-litre ice packs to be replaced every 3 days. Note: never use fewer than 12 0.6-litre ice packs.
► At ambient temperatures above 40°C: 12 0.6-litre ice packs to be replaced every day or 18 0.6-litre ice packs to be replaced every 2 days or 24 0.6-litre ice packs to be replaced every 3 days.
1 Giostyle-type vaccine carrier for 2 preparers can store 500 (3 cm3/dose) to 750 (2 cm3/dose) doses of vaccine and solvent, and requires:
► At ambient temperatures below 40°C: 6 0.4-litre ice packs, to be replaced every day.
► At ambient temperatures above 40°C: 8 0.4-litre ice packs, to be replaced every day.
Additional ice packs and vaccine doses can be supplied by the logistics team during the day, according to needs.
|  |  |  | 3 | 2
2
Check the box corresponding to the outside temperature
Check the box corresponding to the interval for replacing ice packs in the RCW25 cold boxes
The tables below change automatically as a function of the temperature and replacement interval.
Table A: Automatic calculation of the needs for 1 or 2 teams at one site.
PASSIVE COLD CHAIN EQUIPMENT PER SITE |  | Nb of cold boxes and vaccine carriers per team | Nb of ice packs per cold box and vaccine carrier |  |  | Total nb of ice packs on D1 | Volume of ice packs
1 RCW 25 cold-box (vaccines and diluents) |  | 1 | 24 |  |  | 24 | 0.6 l
Vaccine carrier Giostyle for 1 team |  | 1 | 8 |  |  | 8 | 0.4 l
Vaccine carrier Giostyle for 2 teams |  | 2 | 8 |  |  | 16 | 0.4 l
Table B: Automatic calculation of the number of ice packs needed per day for 1 or 2 teams at one site. These numbers are transferred to the table in point 2.
Rythmn and number of ice packs needed
|  |  | D1 | D2 | D3 | D4 | D5
Nb of ice packs required for 1 team per site |  |  | 32 | 8 | 8 | 32 | etc.
Nb of ice packs required for 2 teams per site |  |  | 40 | 16 | 16 | 40 | etc.
2) Estimate the number of ice packs needed each day for all of the teams and sites
Enter the names of the locations and sites (one line per site), the number of teams per site and their identification
Then transfer the number of ice packs needed per day and per site according to the data in Table B (above).
District:
Table C
Towns/locations and sites | Number of teams | Team n° | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23
TOTAL number of ice packs needed per day |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) Determine the available and required freezing capacities
From the inventory, fill in one line in Table D for each type of working freezer available.
Indicate for each brand and type of freezer: number and specifications (freezing capacicty and volume in litres).
3 types of freezers VESTFROST are proposed. Add the other types of freezers available and enter the specifications: freezing capacicty and volume (yellow boxes)
Table D
Brand and type | Number | Freezing capacity | D2: Storage
|  |  |  | Volume (litres) |  | Nb of ice packs
|  | Kg/24 h | D1: Nb ice packs 0.6 l/24 h; D2: Per freezer; D3: Total; D4: Per freezer; D5: Total
VESTFROST MF 314 |  | 32.4 | D1: 0; D2: 323; D3: 0; D4: 323; D5: 0
VESTFROST MF 214 |  | 22.3 | D1: 0; D2: 213; D3: 0; D4: 213; D5: 0
VESTFROST MF 114 |  | 17.5 | D1: 0; D2: 111; D3: 0; D4: 111; D5: 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
TOTAL |  | 72.2 | D1: 0; D2: 647; D3: 0; D4: 647; D5: 0
According to the inventory of available freezers for the campaign:
It is possible to freeze | 0 | ice packs per day
It is possible to store | 0 | ice packs in total
Number of days required to freeze all the ice packs for Day 1 |  |  | D2: #DIV/0!; D3: Note:; D5: do not exceed the freezers' freezing capacity per 24 hours.
Put in half of the ice packs to freeze in the morning and the other half at night.
4) Evolution of ice-packs needs per day for sites
On D1, note the maximum number of ice packs that can be stored (H85, B89) or the maximum number of frozen ice packs available on D1. Any negative quantity means that there will not be enough ice packs to supply all the teams.
|  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24
| Balance (1) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Out (2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In (3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(1) BALANCE = number of available ice packs.
(2) OUT = total number of ice packs supplied to the teams on vaccination sites per day (see point 2).
(3) IN = total number of ice packs that can be frozen per day (see point 3, freezing capacity per 24 h).
Notes | bar: D1 to D10
The performance of all the freezers enables the supply of ice packs to all the sites for 5 days. | bar: D1 to D10
On Day 6, the balance is less than the needs. It is no longer possible to supply the all sites. | bar: D1 to D10
The freezing capacity must be increased (additional freezer and/or other sources of supply) in order to supply all the sites for 10 days as initially planned. | bar: D1 to D10
Note on C96: Note: when the cell becomes gray and the number in black is crossed out, the amount is greater than the number of ice packs cells that can be stored (cells H85, B89).
Température supérieure à 40°C
Température inférieure à 40°C
1 jour
2 jours
3 jours

## Freezing capacity 40 sites
ESTIMATING NEEDS - FREEZING CAPACITY for a vaccination campaign
The volume and freezing capacity needed depend primarily on the number of vaccination sites, the number of vaccination teams per site, and the schedule and duration of the campaign (see sheets "Vaccination schedule by location" and "Vaccination schedule by team").
1) Il faut en premier lieu définir les besoins en glace pour chaque site. Une glacière RCW 25 permet de transporter environ 5000 doses de vaccin avec le solvent. Sachant que l'on estime les performances d'un vaccinateur a environ 1500 vaccinations par jou
FILL IN ONLY THE YELLOW BOXES. Calculations will appear automatically.
1) Define the cold chain equipment for one vaccination site
One vaccination site can accommodate one or two teams, at most (1 to 2 vaccinators, and 2 preparers per vaccinator).
One vaccinator can vaccinate, on average 800 to 1000 vaccinations per day in urban areas and 300 to 600 in rural areas.
Determine the cold-chain needs for each team:
1 RCW 25 cold box (20.4 litres) can store 3300 (3 cm3/dose) to 5000 (2 cm3/dose) doses of vaccine and solvent, and requires:
► At ambient temperatures below 40°C: 12 0.6-litre ice packs to be replaced every 2 days or 14 0.6-litre ice packs to be replaced every 3 days. Note: never use fewer than 12 0.6-litre ice packs.
► At ambient temperatures above 40°C: 12 0.6-litre ice packs to be replaced every day or 18 0.6-litre ice packs to be replaced every 2 days or 24 0.6-litre ice packs to be replaced every 3 days.
1 Giostyle-type vaccine carrier for 2 preparers can store 500 (3 cm3/dose) to 750 (2 cm3/dose) doses of vaccine and solvent, and requires:
► At ambient temperatures below 40°C: 6 0.4-litre ice packs, to be replaced every day.
► At ambient temperatures above 40°C: 8 0.4-litre ice packs, to be replaced every day.
Additional ice packs and vaccine doses can be supplied by the logistics team during the day, according to needs.
|  |  |  | 3 | 1
2
Check the box corresponding to the outside temperature
Check the box corresponding to the interval for replacing ice packs in the RCW25 cold boxes
The tables below change automatically as a function of the temperature and replacement interval.
Table A: Automatic calculation of the needs for 1 or 2 teams at one site.
PASSIVE COLD CHAIN EQUIPMENT PER SITE |  | Nb of cold boxes and vaccine carriers per team | Nb of ice packs per cold box and vaccine carrier |  |  | Total nb of ice packs on D1 | Volume of ice packs
1 RCW 25 cold-box (vaccines and diluents) |  | 1 | 14 |  |  | 14 | 0.6 l
Vaccine carrier Giostyle for 1 team |  | 1 | 6 |  |  | 6 | 0.4 l
Vaccine carrier Giostyle for 2 teams |  | 2 | 6 |  |  | 12 | 0.4 l
Table B: Automatic calculation of the number of ice packs needed per day for 1 or 2 teams at one site. These numbers are transferred to the table in point 2.
Rythmn and number of ice packs needed
|  |  | D1 | D2 | D3 | D4 | D5
Nb of ice packs required for 1 team per site |  |  | 20 | 6 | 6 | 20 | etc.
Nb of ice packs required for 2 teams per site |  |  | 26 | 12 | 12 | 26 | etc.
2) Estimate the number of ice packs needed each day for all of the teams and sites
Enter the names of the locations and sites (one line per site), the number of teams per site and their identification
Then transfer the number of ice packs needed per day and per site according to the data in Table B (above).
District:
Table C
Towns/locations and sites | Number of teams | Team n° | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23
TOTAL number of ice packs needed per day |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) Determine the available and required freezing capacities
From the inventory, fill in one line in Table D for each type of working freezer available.
Indicate for each brand and type of freezer: number and specifications (freezing capacicty and volume in litres).
3 types of freezers VESTFROST are proposed. Add the other types of freezers available and enter the specifications: freezing capacicty and volume (yellow boxes)
Table D
Brand and type | Number | Freezing capacity | D2: Storage
|  |  |  | Volume (litres) |  | Nb of ice packs
|  | Kg/24 h | D1: Nb ice packs 0.6 l/24 h; D2: Per freezer; D3: Total; D4: Per freezer; D5: Total
VESTFROST MF 314 |  | 32.4 | D1: 0; D2: 323; D3: 0; D4: 323; D5: 0
VESTFROST MF 214 |  | 22.3 | D1: 0; D2: 213; D3: 0; D4: 213; D5: 0
VESTFROST MF 114 |  | 17.5 | D1: 0; D2: 111; D3: 0; D4: 111; D5: 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
|  |  | 0 |  | 0 | 0 | 0
TOTAL |  | 72.2 | D1: 0; D2: 647; D3: 0; D4: 647; D5: 0
According to the inventory of available freezers for the campaign:
It is possible to freeze | 0 | ice packs per day
It is possible to store | 0 | ice packs in total
Number of days required to freeze all the ice packs for Day 1 |  |  | D2: #DIV/0!; D3: Note:; D5: do not exceed the freezers' freezing capacity per 24 hours.
Put in half of the ice packs to freeze in the morning and the other half at night.
4) Evolution of ice-packs needs per day for sites
On D1, note the maximum number of ice packs that can be stored (H85, B89) or the maximum number of frozen ice packs available on D1. Any negative quantity means that there will not be enough ice packs to supply all the teams.
|  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24
| Balance (1) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Out (2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| In (3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(1) BALANCE = number of available ice packs.
(2) OUT = total number of ice packs supplied to the teams on vaccination sites per day (see point 2).
(3) IN = total number of ice packs that can be frozen per day (see point 3, freezing capacity per 24 h).
Notes | bar: D1 to D12
The performance of all the freezers enables the supply of ice packs to all the sites for 5 days. | bar: D1 to D12
On Day 6, the balance is less than the needs. It is no longer possible to supply the all sites. | bar: D1 to D12
The freezing capacity must be increased (additional freezer and/or other sources of supply) in order to supply all the sites for 10 days as initially planned. | bar: D1 to D12
Note on C117: Note: when the cell becomes gray and the number in black is crossed out, the amount is greater than the number of ice packs cells that can be stored (cells H85, B89).
Température supérieure à 40°C
Température inférieure à 40°C
1 jour
2 jours
3 jours